## Slide 1: The ID as Project Manager
Managing a Project When You’re NOT the Boss

## Slide 2: Clay Alan Ham, PhD, PMP
HE & HE Administration
HE Accreditation
SC K-12 Online Program
QM K-12/CPE Master Reviewer
Certified PMP
cham@ed.sc.gov

## Slide 3: How do you like “group work”?
- In less than 60 seconds … Yes? No? Maybe? -

## Slide 4: To group or not group?
To group or not to group?

## Slide 5: Your best team experience?
- In less than 60 seconds … Who? What? Outcome? -

## Slide 6: Session Description
Instructional Designer …
… completing the course
... managing a cross-functional team.

## Slide 7: ID as Project Manager
Project management:
“The application of knowledge, skills, tools, and techniques to project activities to meet the project requirements.”
pmi.org

## Slide 8
You should be able to:
Explain PM lingo …
Employ PM resources …
Evaluate project deliverables …

## Slide 9: Talking like a Project Manager

## Slide 11: PM Lingo Matching (1)
Project
Deliverable
Scope
Resource
All the work and only the work to be done
Temporary group of tasks to create a new product
Product(s) produced as a result of the project
Anything necessary for completing the project

## Slide 12: PM Lingo Matching (2)
Constraint
Risk
Acceptance
Stakeholder
Person/Group whose interest is affected by the project
Approval when project meets quality requirements
Factor which limits the ability to plan
Unknown event/condition which may affect the project

## Slide 13: Which word?
Acceptance
Constraint
Deliverable
Resource
Risk
Stakeholder
Completed master course ready to copy for instructor facilitation
Completed by the master copy deadline prior to the beginning of the semester
Office closure for hazardous weather
Student, parent, and teacher
Meets quality standards (e.g., QM Rubric)
ID and Subject Matter Expert

## Slide 14: Who are your stakeholders?
- In less than 60 seconds … Whose interest is affected? -

## Slide 15: 50%
Percentage of conflict that arises because of schedules, resources, and priorities.
Andy Crowe, The PMP Exam (5th ed.)

## Slide 16: Managing the Project Team

## Slide 17: Triple Constraint
Work/Quality
Schedule
Resources

## Slide 18: 95 Deliverables
3 Phases
Design
Develop
Document

## Slide 21: Design Course
Course/Unit Plans
Course Objectives
Final Assessments
Scope/Sequence of Units
Unit Objectives
Unit Assessments
Scope/Sequence within Units
Alignment to Standards

## Slide 22: Develop Course
Unit Content
Assessments
Resources
Media
Activities
Tools
Framing for students
Grading Criteria
Instructions for LMS

## Slide 23: Document Course
Course Documentation
Syllabus
Standards Alignment
Instructor Guide
Accommodations
Course Links

## Slide 24: Schedule
Dealing with time

## Slide 25: Gantt Chart
Shows project schedule
Marks the Critical Path
… to keep SME working!

## Slide 26: Improve course projects?
- In less than 60 seconds … Scope? Schedule? -

## Slide 27: IDs as PMs help the team create realistic deadlines and ensure the course project stays on schedule.

## Slide 28: 50%
Percentage of conflict that arises because of schedules, resources, and priorities.

## Slide 29: Managing the Project Team

## Slide 30: Who’s on team?
- Subject Matter Expert -

## Slide 31: Project Manager
Noun. [pruh-jekt man-ijer]
Someone who solves a problem you didn’t know you had in a way you don’t understand.
See also wizard, magician

## Slide 32: Leading a team when you’re not the boss

## Slide 34: Project Team
Managing
motivation, power, conflict,
and communication

## Slide 35: Develop the Project Team

## Slide 36: “Ladder of Team Development”
Bruce Tuckman, Developmental Sequence in Small Groups, Psychological Bulletin 63(6), (1965), 384-399.
Judith Stein, Using the Stages of Team Development, Learning & Development, HR at MIT

## Slide 37: Tools for Develop Project Team
Five tools:
Interpersonal skills (aka “soft skills”)
Training
Team-building activities
Ground rules
Theories of motivation

## Slide 38: What do SMEs Need?
What do these needs suggest about …
- how we relate to SMEs?
- how we motivate SMEs?

## Slide 39: Herzberg’s Motivation-Hygiene Theory
What factors influence satisfaction at work?
Hygiene factors OR Motivation Factors

## Slide 40
Drive:
the surprising truth
about
what motivates us
by
Daniel
Pink

## Slide 41: Manage the Project Team

## Slide 42: Forms of Power
Expert
Legitimate
Punishment
Referent
Reward

## Slide 43: Tools for Manage Project Team
Five tools:
Interpersonal skills
Communication
Schedule
Constructive and destructive team roles
Conflict management

## Slide 44: Constructive and Destructive Team Roles
Initiators
Information Seekers
Blockers
Recognition Seekers
Clarifiers
Withdrawers
Gate Keepers
Dominators
Encouragers
Information Givers
Topic Jumpers
Aggressors
Summarizers
Harmonizers
Devil’s Advocates

## Slide 45: Conflict?
Collaboration
Compromise
Forcing
Problem-solving
Smoothing
Withdrawal

## Slide 46: Challenging team experience?
- In less than 60 seconds … What takeaway will you try? -

## Slide 47: IDs as PMs have limited authority and must influence through listening, persuading, and building trusting relationships.

## Slide 48: 50%
Percentage of conflict that arises because of priorities, schedules, and resources.

## Slide 49: Evaluating Project Deliverables

## Slide 50: Quality Assurance
Scope Definition
Acceptance Criteria
Review Procedures
Course Acceptance

## Slide 51: Scope
Definition -- What IS a completed course?
Acceptance Criteria -- Does the course meet QUALITY standards?
Backwards-Design
Aligned with standards
VSC Course Template
QM standards
Legal regulations (e.g., copyright)
Accessible and readable
Documentation

## Slide 52: Quality Control
Clear design
Well written
Alignment
Assessments
Instructional material
Activities
Tools
Accessibility

## Slide 53: Acceptance
Review by Project Sponsor
___
Completed Master Course
Backwards-Design
Aligned with standards
VSC Course Template
QM standards
Legal regulations
Accessible and readable
Documentation

## Slide 54: Quality assurance?
- In less than 60 seconds … How can your process improve quality?

## Slide 55: IDs as PMs guide the design team through a review process to ensure the project produces a quality course.

## Slide 56: Continuous Improvement
“Continuous improvement is better than delayed perfection” -- Mark Twain
"Quality is not an act, it is a habit.” -- Aristotle
"If you can't describe what you are doing as a process, you don't know what you're doing” -- W. Edwards Deming

## Slide 57
Clay Alan Ham
cham@ed.sc.gov